## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Dark
Genesis Configuration Management
Boeing |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Douglas Swanson
Project Start Date: | 2022-10-17 |  |  |  |  | October | [20 empty] | November | [27 empty] | December
Scrolling Increment: | 0 | time axis 2022-10-17 to 2022-12-11
Milestone description | Category | Assigned to | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Project Dealine | Goal | Doug | 0% | 2022-11-19 | 1 | S: 2
Research and Data Modeling | Milestone | Doug | 100% | 2022-09-05 | 30
Genesis Scenario Management Service | Milestone | Doug | 30% | 2022-10-17 | 7 | bar: M to S
Build CRUD Service | On Track | Doug | 70% | 2022-10-17 | 5
Write Unit Tests | Goal | Doug | 0% | 2022-10-21 | 3 | F: 2; S: 2; S: 2
Write Documentation | Goal | Doug | 0% | 2022-10-21 | 3 | F: 2; S: 2; S: 2
Scenario Spacecraft Service | Milestone | Doug | 10% | 2022-10-24 | 4 | bar: M to T
Build CRUD Service | On Track | Doug | 25% | 2022-10-24 | 2
Write Unit Tests | Goal | Doug | 0% | 2022-10-26 | 2 | W: 2; T: 2
Write Documentation | Goal | Doug | 0% | 2022-10-26 | 2 | W: 2; T: 2
Genesis Service Broker | Milestone | Doug | 0% | 2022-10-28 | 5 | bar: F to T
Define Data Model | On Track | Doug | 50% | 2022-10-28 | 1
Write Registration Logic into Services | Goal | Doug | 0% | 2022-10-29 | 3 | S: 2; S: 2; M: 2
Write Service Information Gathering Logic | Goal | Doug | 0% | 2022-10-30 | 3 | S: 2; M: 2; T: 2
Genesis Frontend | Milestone | Doug | 0% | 2022-11-02 | 10 | bar: W to F
NodeJs server | Goal | Doug | 0% | 2022-11-02 | 5 | W: 2; T: 2; F: 2; S: 2; S: 2
React UI | Goal | Doug | 0% | 2022-11-07 | 5 | M: 2; T: 2; W: 2; T: 2; F: 2
Documentation and Testing | Milestone | Doug | 0% | 2022-11-12 | 7 | bar: S to F
To add more data, Insert new rows ABOVE this one